## Work Structure
Phase | Category | Checkbox | Target Date | Date Completed | Index | TASK | Output
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 1 | Team Introduction & Setup | Vineet , Mariel , Kousar , Joe
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 2 | Define The problem | RCHG Wants to Launch LMS to centralize learning efforts and leverage data driven insights to improve staff training , compliance , and performances.
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 3 | Understand the project | Deliver analytical solution for RCHG using the LMS data. That answer the 7 Business Questions and proving by Statistical Techniques.
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 4 | Identify Key Business Questions | Identified 21 Key Questions Refer to [Table] Business Questions
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 5 | Define the Success Criteria | Identified 6 Success Criteria
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 6 | Set-up and Requirements | Identified tools to complete the project
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 7 | Upload Dataset | GITHUB LINK
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 8 | Understand the data | 3 Dataset , 22x2001 , 3x19 , 4x958
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 9 | Data Cleaning | Perfrom Data cleaning Steps
PHASE 1 | Define | TRUE | 2025-07-23 | 2025-07-23 | 10 | Upload Clean Dataset for the team | GITHUB LINK
PHASE 2 | Model | TRUE | 2025-07-24 | 2025-07-24 | 1 | Determine Data Architecture | Snowflake schema for efficient and eliminate redundancy
PHASE 2 | Model | TRUE | 2025-07-24 | 2025-07-24 | 2 | Design dimension table and fact table | Data Modeling
PHASE 2 | Model | TRUE | 2025-07-24 | 2025-07-24 | 3 | Import Data and Manage Relationship | Done in PowerBi GITHUB LINK
PHASE 2 | Model | TRUE | 2025-07-24 | 2025-07-24 | 4 | Data Model Validation | Done in PowerBi GITHUB LINK
PHASE 3 | Analysis | TRUE | 2025-07-25 | 2025-07-25 | 1 | Statistical Analysis | Done in PowerBi GITHUB LINK
PHASE 3 | Analysis | TRUE | 2025-07-25 | 2025-07-25 | 2 | Business Question Analysis | Done in PowerBi GITHUB LINK
PHASE 3 | Visualization | TRUE | 2025-07-25 | 2025-07-26 | 3 | Power BI Data Model Setup | Done in PowerBi GITHUB LINK
PHASE 3 | Visualization | TRUE | 2025-07-25 | 2025-07-26 | 4 | Dashboard Development | Done in PowerBi GITHUB LINK
PHASE 3 | Visualization | TRUE | 2025-07-26 | 2025-07-27 | 5 | Dashboard Testing & Validation | Done in PowerBi GITHUB LINK
PHASE 4 | Insights | TRUE | 2025-07-26 | 2025-07-27 | 1 | Key Findings | Done By Vineet
PHASE 4 | Insights | TRUE | 2025-07-28 | 2025-07-27 | 2 | Business Analysis | Done By Vineet
PHASE 4 | Insights | TRUE | 2025-07-28 | 2025-07-27 | 3 | Recommendations | Done By Vineet
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-28 | 1 | Technical Documentation | Done By Vineet
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-29 | 2 | Business Report Writing | Done by Kousar
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-29 | 3 | README & Repository Documentaion | Done by Kousar
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-29 | 4 | Team Collaboration Reflection | Done By Vineet
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-30 | 5 | Final Review | Done By All
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-30 | 6 | Submission | Done By All
PHASE 5 | Documentation | TRUE | 2025-07-28 | 2025-07-30 | 7 | Linkedin Posting | Done By All

## Team_Members
Team Members | Strength / Weakness | Roles | Core Function
Vineet | SQL / PowerBI | Data Analyst | Data Architecture and Data Modeling
Mariel | Python / SQL | Data Analyst | Programming & Statistical Analysis
Kousar | Python / PowerBI | Data Analyst | Business Insight Report & Analysis
Joe | PowerBI / Python | Data Analyst | Data Visualization & Project Organizer

## Success Criteria
Column1 | Column2
Index | Success Criteria
1 | Clean raw data
2 | Data Model Architecture
3 | PowerBI dashboard answering Business questions
4 | Insights and recommendation
5 | Top-Down Documentation
6 | Project Completion Before July 28

## Business Questions
Key Business Questions | 1. What is the current completion rate of mandatory courses across departments and locations?
2. How actively are employees engaging with the LMS? (Devices used, duration, access patterns, etc.)
3. What trends are evident in skill development, feedback, and review scores?
4. Are there statistically significant differences in skill scores across teams or roles?
5. Can we predict future training needs or compliance risks using historical data?
6. How do course engagement levels relate to performance review outcomes?
7. What actionable insights can drive future learning strategies?
Compliance & Training Summary | 8. What is the Percentage of completed mandatory courses By Team and Department?
9. What is the overdue training over time ?
Performance Analysis | 10. What is the distribution of SkillCore Ratings across teams and roles ?
11. What is the most flagged Skill gaps?
12. What is the average review scores and review frequency?
Engagement Patterns | 13. Over all Time spent to complete each course? ( enrollment date - Last Access date )
14. Time spent to complete each course by role ? ( enrollment date - Last Access date )
15. Time spent to complete each course by location? ( enrollment date - Last Access date )
16. Most Used Device?
Statistical Analysis | 17. Predict the training completions for next quarter
18. Create a model impact of training time vs Frequency on performance scores
19. Cmapre Mean Skill score across multiple depratments to identify statistically significant performance disparities.
Accessibility | 20. What is the population of users who accessed training using screen reader and their respective performance?
21. Comparison of feedback scores vs accessibility scores ?

## Set-up & Requirements
Tools | Purpose | Column Name | Description
Excel | Data Cleaning And Exploration Analysis | EmployeeID | Unique identifier assigned to each employee
Python | Statistical Analysis | FirstName and LastName | First and last name of the employee
PowerBI | Data Modeling & Data visualization | Email Address | Employee's official email address
Word Document | Report Summary | Team | The department or functional team the employee belongs to
PDF Format | Report Submission | Role | The job title or designation of the employee
Documentation | Excel & Github | Location | Office or branch location where the employee is based
Project Management | Excel & Github Kanban | JoinedDate | Date the employee joined the organization
|  | CourseID | Unique identifier for each training course
|  | CourseTitle | Name of the course undertaken by the employee
|  | CourseCategory | Category or domain of the course (e.g., Compliance, Health & Safety)
|  | CourseProvider | The platform or vendor delivering the course (e.g., Cornerstone, LinkedIn)
|  | IsMandatory | Indicates whether the course is mandatory (Yes/No)
|  | EnrollmentDate | Date the employee was enrolled into the course
|  | CompletionDate | Date the employee completed the course (if completed)
|  | CompletionStatus | Status of the course (e.g., Completed, Overdue)
|  | Score | Final score or result the employee received in the course (if applicable)
|  | DurationMinutes | Total time (in minutes) the employee spent on the course
|  | LastAccessDate | Date the employee last accessed the course
|  | AccessedViaDevice | Device used to access the course (e.g., Mobile, Tablet, Desktop)
|  | SkillScore_Communication | Rating (typically 1–5) for communication skills
|  | SkillScore_TechEfficiency | Rating (typically 1–5) for technical efficiency
|  | SkillScore_Teamwork | Rating (typically 1–5) for teamwork skills
|  | SkillGapFlag | Indicates whether a skill gap was flagged during performance review (Yes/No)
|  | FeedbackComment | Verbal or written feedback about the course from the employee
|  | FeedbackRating | Numeric rating (typically 1–5) given by the employee for the course
|  | UsedScreenReader | Indicates whether the employee used a screen reader to access the course (Yes/No)

## Data Cleaning
Steps | Column | Action | Notes
Standardized Dates | JoinedDate | YYYY-MM-DD | Good
Standardized Dates | EnrollmentDate | YYYY-MM-DD | Good
Standardized Dates | CompletionDate | YYYY-MM-DD | Good
Standardized Dates | LastAccessDate | YYYY-MM-DD | Good
Clean Categories | IsMandatory | Replace No (30) => No | Good
Clean Categories | FeedbackRating | Replace Very Useful : 4 => Very Useful : 3 | Good
Clean Null Values | Score | Replace Null Values to 0 | Good
Clean Null Values | CompletionDate | Replace Null Values to 1911-01-01 | Good
Clean and Trim | All | Trim whitespaces | Good
Create IsCompleted | IsCompleted | Bolean Value if Course is Completed | Good
Create DaytoComplete | Daystocomplete | Calculate duration Completiondate - EnrollmentDate | Good

## Data Analysis
Question | Category | Measure | Categorize By | Column1
1 | Completion Rate | Count total course | Departments & Locations
1 | Completion Rate | Count total completed | Departments & Locations
1 | Completion Rate | Count completion rate | Departments & Locations
1 | Completion Rate | Count Mandatory course | Departments & Locations
1 | Completion Rate | Count Mandatory completion rate | Departments & Locations
2 | Engagement | Count total course | Device Type & ScreenReader
2 | Engagement | Count total Course Sessions | Device Type & ScreenReader
2 | Engagement | Count Average Diration | Device Type & ScreenReader
3 | Trends | How Employees change Over time ( Quarterly ) | Score , Skill ( Teamwork , Communication , Technical Efficiency ) , Feedback , Skillgap
3 | Trends | Average score | Score , Skill ( Teamwork , Communication , Technical Efficiency ) , Feedback , Skillgap
3 | Trends | Average SkillsScore | Score , Skill ( Teamwork , Communication , Technical Efficiency ) , Feedback , Skillgap
3 | Trends | Average Feedback | Score , Skill ( Teamwork , Communication , Technical Efficiency ) , Feedback , Skillgap
3 | Trends | Count of Skillgap | Score , Skill ( Teamwork , Communication , Technical Efficiency ) , Feedback , Skillgap
4 | Statistical differences | Anova Analysis : Average of Score By 6 Teams | Score & Skill ( Teamwork , Communication , Technical Efficiency ) By Teams & Roles | Reference : https://www.youtube.com/watch?v=2l-ZnfTbKhg
4 | Statistical differences | Anova Analysis : Average of Skills By 6 Teams | Score & Skill ( Teamwork , Communication , Technical Efficiency ) By Teams & Roles
4 | Statistical differences | Anova Analysis : Average of Score By 19 Roles | Score & Skill ( Teamwork , Communication , Technical Efficiency ) By Teams & Roles
4 | Statistical differences | Anova Analysis : Average of Skills By 19 Roles | Score & Skill ( Teamwork , Communication , Technical Efficiency ) By Teams & Roles
5 | Predictive Model | Predictive analysis : Q3 2025 - Q4 2026 Completion rate | Overall Completion Rate By Quarter | Regression Analysis
5 | Predictive Model | Predictive analysis : Risk Assessement | Overall Completion Rate By Quarter | Regression Analysis
6 | Course Engagement vs performance Review | Predictive analysis : | - | Regression Analysis
7 | Future Insights | Predictive analysis : | -
Page | Dashboard | Measure | Charts
All | Compliance & Training | %Total Course Completed | CARD
All | Compliance & Training | %Total Mandatory Course Completed | CARD
All | Compliance & Training | %total Overdue | CARD
All | Compliance & Training | Average Score | CARD
All | Compliance & Training | Average SkillScore | CARD
All | Compliance & Training | Average Feedback | CARD
1 | Compliance & Training | Course Mandatory | Slicer
1 | Compliance & Training | Course Count & %completed by team | Column Graph
1 | Compliance & Training | Course Count & %completed by department? Role? Or location? | Bar Chart
1 | Compliance & Training | Overdue Count & %Overdue per quarter | Line Chart
2 | Performance Analysis | SkillScore Ratings By 6 Teams Skillscore Avg + Teamwork + Communication + Efficiency | Column Graph
2 | Performance Analysis | SkillScore Ratings By 19 Roles Skillscore Avg + Teamwork + Communication + Efficiency | Bar Chart
2 | Performance Analysis | Count of skilledflag by course | Bar Chart
2 | Performance Analysis | average Review Score and Review Frequency ? Refering to Review = 19 course? Review Frequency = Total count of Each Course taken. | Column Graph
3 | Engagement patterns | duration on each course ( 19 courses) By Role 19 roles | column graph
3 | Engagement patterns | duration on each course ( 19 courses) By location 4 location | column graph
3 | Engagement patterns | count of enrollment per quarter | line graph
3 | Engagement patterns | count of lastaccess per quarter | line graph
3 | Engagement patterns | Most used device Distribution ( 3 devices ) + Devices with screenreader | Donut with screenreader slicer
4 | Statistical Analysis | Quarterly Completion rate : predict 2025-2026 quarter | Line Chart
4 | Statistical Analysis | Regession analysis : Training time & Frequency Vs Performance score | table
4 | Statistical Analysis | Anova : Mean skillscores per department | table
5 | Accessibility | Count of employee screen reader vs Non-screen reader | Donut chart + card
5 | Accessibility | Avg Feedback scores of reader vs Non screen reader | Donut chart + card
5 | Accessibility | Count of Accessibility by courses | Bar Chart
5 | Accessibility | Count of Accessibility by Team | Bar Chart

## Data Visualization
Page 1
Page 2
Page 3
Page 4
Page 5